*DRAFT DOCUMENT FOR CONSULTATION*

Over recent months a range of professionals, community members and interested parties have been working together to draft an idea of what North East Lincolnshire’s vision is for those with dementia and their carers. The discussions have included looking at the gaps, areas for improvement and what to date has worked well.

The draft Vision and Forward Plan are detailed below. We would like to widen our engagement to include all of those in North East Lincolnshire with dementia and their carers, wider professional groups and the community as a whole. We would really welcome your comments on the Vision and Forward Plan. Please could you comment on the following questions, returning your answers by post, email or by telephone as detailed below?

- a. Do you agree with the Vision we have written below?

b. If not, how would you change the Vision?

2. a. Are there any other gaps that have not been identified that you would like included?

b. If so, what are the gaps?

3. a. Does the Action Plan include all actions you wish to see for the next year?

b. If not, which actions are missing?  And who should be responsible for that action/s?

4. Do you have any further comments on the Vision and Forward Plan?

Please send all responses using your preferred method:

0300 3000 428 / amy.tristman@nhs.net

FAO Amy Tristman, NEL Clinical Commissioning Group, Athena Building, 5 Saxon Court, Gilbey Road, Grimsby, DN31 2UJ

Please note that the deadline for sending feedback is 19th Feb

Dementia Vision and Forward Plan

Vision

“It is our vision that all people living with dementia in North East Lincolnshire live well, by:

| - Having access to appropriate information, advice and support at the right time - Receiving a timely diagnosis, in a place appropriate to their needs - Having a range of on-going support available to them - Receiving excellent care from diagnosis to end of life | - Receiving support from staff expertly trained in dementia, whether the person is at home, in a care home or in hospital - Carers and family members being supported to sustain their caring role while having a life outside of caring |
| --- | --- |

This will all be delivered through integrated partnerships, creating a dementia friendly North East Lincolnshire.”

Achievements to Date

Gaps/ Areas for Improvement

| - Improved access and reliability of transport support for those with dementia and their carers is required - There is a need to ensure appropriate facilities and services for those with dementia and their carers across NEL, as part of dementia friendly communities - Further development of the Dementia Action Alliance is required - There is a need for advocacy & mediation support – a voice to help support those with dementia and their carers - Improvement/ review of the Dementia pathway, to ensure the role of Primary Care in the management and diagnosis of dementia. In addition, the Alzheimer’s Society should be able to refer into services following diagnosis (this will eliminate the need for re-referrals) and signpost people to post diagnostic support. - We need a greater number of awareness raising campaigns around the signs and symptoms of dementia and in particular more awareness of early onset dementia - A reduction in inappropriate anti-psychotic drug prescribing and the issues with these drugs across a variety of care environments (e.g. care homes) is required - We should develop a Dementia Directory for NEL to replace the Dementia Portal, managed and updated by the Alzheimer’s Society - The profile of the Dementia GP toolkit should be raised and we should ensure GP sign up - There should be two Dementia newsletters, co-ordinated by the Alzheimer’s Society - 1 for service users and 1 for professionals - Improve GP, Social Care and Health professionals’ (hospital, ambulance, social workers, care homes, domiciliary care staff) awareness and understanding of dementia through training and awareness raising - Ensure targeted support for those with early onset dementia is available |  |  | - An end of life pathway is needed for those with dementia - We should focus on improving physical health and ensuring that it is not ignored post diagnosis for those with dementia, as well as supporting carers’ wellbeing - Hospital admissions should be properly assessed and their needs cared for – effective liaison into general hospital and intermediate tier services - More in county specialist nursing care for those with dementia is required - Integrated record sharing is needed to ensure consistency of care – Health/Mental Health/Social Care - All organisations/relevant stakeholders/ those with dementia and their carers should be involved when planning service design, delivery and monitoring - We should keep information current, up to date and relevant using a variety of formats – leaflets, posters, websites, email and the media - We must improve sharing of information between agencies and organisations - Improved liaison between services – there is a potential development in role for voluntary sector staff working with specialist services - There should be a mechanism to ensure appropriate and efficient use of resources, integrated working and no duplication - New creative alternatives to providing support should be developed, i.e. blogs – social media - There should be one point of contact (Alzheimer’s Society) after diagnosis - A review of respite and crisis beds is needed - improved quality, availability and flexibility - Training for families/ carers should be progressed - Research needs to inform our local dementia vision and strategy |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Action Plan |  | By Who | By When | Progress |  |
| Raising Awareness & Understanding | Refocus of DAA to ensure that the way forward is clear and support is in place for the DAA to carry out its functions |  | AS/DAA | 01.06.16 |  |  |
|  | To raise awareness across NEL on all aspects of dementia and encourage citizens to actively identify/ accomplish actions which support the Dementia Agenda |  | DSG/ DAA | On-going |  |  |
|  | Provision of awareness raising training to promote understanding and awareness of dementia |  | DSG/ DAA | On-going |  |  |
|  | Promotion of the Dementia Help Card |  | AS | On-going |  |  |
|  | Work to ensure that NEL becomes dementia friendly – libraries, public facilities, community centres, transport |  | DAA | 31.03.17 |  |  |
|  | Support all GP practices to become dementia friendly |  | DAA | 31.03.17 |  |  |
|  | Local implementation/ support of national and local initiatives such as Dementia Awareness Week events, dementia campaigns and promotions |  | DSG | On-going |  |  |
|  | Awareness raising campaigns for: signs and symptoms of dementia (supporting those with recognised dementia and signposting to GPs those with potential symptoms), dementia diagnosis, early onset dementia |  | AS | 31.03.17 |  |  |
|  | Ensure research is a regular feature on the Dementia newsletter |  | AS | On-going |  |  |
|  | Raise awareness of the new Dementia pathway and use of the Dementia Toolkit for GPs |  | DL, Nav | 30.09.16 |  |  |
|  | Promote the role of the Dementia Advisor and the Alzheimer’s Society as the first point of contact |  | AS, DL | 30.09.16 |  |  |
|  | Promote the role of the NEL Carers’ Support Service as support for carers of those with dementia |  | CL | On-going |  |  |
|  | Raise awareness of the support and services available to those with dementia and their carers at different stages of the dementia journey |  | DSG/ DAA | On-going |  |  |
|  | Develop innovative and creative methods to raise awareness of dementia – social media e.g. blogs |  | AS/ DAA | 31.03.17 |  |  |
|  | Further develop the Dementia Action Alliance and improve the range of organisations/ businesses signed up with action plans |  | DAA/ AS/ DL | 31.04.17 |  |  |
|  | Raise awareness and understanding of Dementia Connect |  | AS | 31.12.16 |  |  |
| Advice, Information & Guidance | Provision of up-to-date, timely and accurate advice and information using a range of formats including leaflets, newsletters, posters, email, websites and the local media |  | DSG | On-going |  |  |
|  | Delivery of a quarterly newsletter – one for professionals and one for those with dementia and their carers |  | AS | On-going |  |  |
|  | Ensure the provision of specialist advice and information for those with dementia and their carers – Admiral Nurse service, Advocacy services, benefits advice etc. |  | Nav, AS, F, DL, NLaG. CPG | 30.09.16 |  |  |
|  | Develop and keep up to date a dementia friendly central information point (Dementia Directory) to replace the current Dementia Portal as a one stop place for all information relating to dementia |  | DSG/ DL | 31.12.16 |  |  |
|  | Develop innovative and creative methods to provide advice, information and guidance – social media e.g. blogs |  | AS/ DAA | On-going |  |  |
|  | Ensure robust partnership working to promote each other’s services and support, and the sharing of information (leaflets) across the full range of organisations and agencies |  | DL | On-going |  |  |
|  | Ensure wherever possible integrated client record sharing to ensure seamless and consistent care |  | Nav/ DL | On-going |  |  |
| Timely Diagnosis & Effective Post Diagnostic Support | Ensure a timely investigation for all those with suspected dementia to ensure earliest possible diagnosis |  | PC | On-going |  |  |
|  | Ensure all those with a dementia diagnosis are referred onto the Dementia pathway |  | PC | On-going |  |  |
|  | Ensure all those with dementia and their carers with an appearance of social care need have a needs based assessment |  | focus | 31.03.17 |  |  |
|  | Further improve the dementia diagnosis rate in North East Lincolnshire from the 2015/16 figure by working with those practices with low prevalence rates |  | DL | 31.03.17 |  |  |
|  | Improve the range of targeted support for those with early onset dementia |  | Nav | 31.03.17 |  |  |
|  | Further improve the range of support for those with dementia post diagnosis and their carers, including physical and emotional support and encouragement to remain/become more active |  | AS, Nav, DL | 31.03.17 |  |  |
|  | Improve the support to those with dementia and their carers on admittance, stay and discharge from hospital and intermediate tier services |  | NLaG/ CPG | 31.03.17 |  |  |
|  | Ensure there is one point of contact after diagnosis – the preference is the Alzheimer’s Society |  | AS, DL | 31..07.16 |  |  |
|  | Ensure the Alzheimer’s Society can navigate back and forth through the system without re-referral via the GP |  | DL, AS | 31.07.16 |  |  |
|  | Review respite, crisis and Enhanced Dementia Bed services including nursing provision for those with dementia |  | NELCCG | 31.03.17 |  |  |
| End of Life Care | Develop a clear pathway for those with dementia at end of life and their carers |  | Nav, DL, EofL | 31.03.17 |  |  |
|  | Ensure that those with dementia at end of life are appropriately supported through integrated working |  | EofL, DL | 31.03.17 |  |  |
| Carers’ Support | Ensure carers of those with dementia are identified, recognised for their role, knowledge and contribution and encouraged to be registered with appropriate services to support their needs, including the North East Lincolnshire Carers’ Support Service and the Alzheimer’s Society |  | CL | On-going |  |  |
|  | Ensure carers of those with dementia are referred for a Carer’s Needs Assessment where they have an appearance of need or are requesting an assessment |  | CL | On-going |  |  |
|  | Ensure carers/ family members of those with dementia are appropriately trained to undertake their caring role as well as support those with dementia effectively |  | CL | On-going |  |  |
|  | Continue to improve the range and quality of carers’ support services |  | CL | On-going |  |  |
|  | Embed the NEL Carers’ Support Service into the Dementia pathway |  | DL | 31.07.16 |  |  |
| Skilled, Knowledgeable and Effective Workforce | Provide awareness raising and training to improve GP, Social Care and Health professionals’ (hospital, ambulance, social workers, care homes, domiciliary care staff) awareness and understanding of dementia in all areas (the symptoms, pain management, managing behaviour etc.) |  | AS/ DL/Nav | On-going |  |  |
|  | Reinforce the educational information available to Health and Social Care professionals to support the continued appropriate use of anti-psychotic drug prescribing |  | DAA | On-going |  |  |
|  | Provide specific training to professionals working with those with dementia and their carers, to ensure consistent, good quality dementia care |  | AS/ Nav | 31.03.17 |  |  |
|  | Development of seamless pathways between services to ensure effective care – e.g. Alzheimer’s Society working effectively with the Home from Home service to ensure continuation of care/ support |  | Nav/ AS | 31.03.17 |  |  |
|  | Agreement and implementation of the two local Dementia CQUINS |  | DL/ NLaG | 31.03.17 |  |  |

| Inclusion in Service Design, Delivery & Monitoring |  | Further develop the Dementia Steering Group as the key driving force for the Dementia Agenda in NEL – revision of the Terms of Reference & inclusion of new membership |  |  | DSG | 30.05.16 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Ensure in all service redesign and development that there is appropriate and efficient use of resources, partnership working and a lack of duplication |  |  | DL | On-going |  |
|  |  | Continue to develop forums to ensure those with dementia and their carers have an active voice locally, by supporting the forums with new membership and on-going delivery |  |  | AS/Nav | On-going |  |
|  |  | Develop an involvement framework for those with dementia and their carers, and encourage those with dementia and their families/ carers to participate in the development of shaping the delivery of local dementia and carers services, through greater recognition and direct invitation to participate in the process, i.e. running planning/ development sessions as service gaps are noted, annual consultation |  |  | DSG/DL | 30.09.16 |  |
|  |  | Develop training /support to those with dementia and their carers /former carers to contribute at a strategic level and become designers, developers and evaluators of local support and services |  |  | DL | On-going |  |
|  |  | Ensure those with dementia & their carers are recognised and continuously thought of when changes are made in all aspects of health and social care, as well as ensuring their inclusion and feedback is directly included in designing, delivery and monitoring of services |  |  | DL | On-going |  |
|  |  | Ensure professionals and wider stakeholders are included in design, development, delivery and monitoring of services |  |  | DL | On-going |  |
| Key: |  |  |  |  |  |  |  |
| - AS - CL - DAA - DL - NELCCG - NLaG | Alzheimer’s Society Carers’ Lead Dementia Action Alliance Dementia Lead NEL Clinical Commissioning Group Northern Lincolnshire & Goole Hospital NHS Foundation trust |  | - DSG - EofL - Nav - PC - F - CPG | Dementia Strategy Group End of Life Lead NAViGO Primary Care Focus Care Plus Group |  |  |  |